## landscape
Long Range Building Program | [8 empty] | 2010-2011 Biennium
Capital Projects Detail
Department: |  | THE UNIVERSITY OF MONTANA
Project Title: |  | Renovation of Second Floor of The Clapp Building | [5 empty] | Statewide Priority: | NA
Brief Description of Project: | [7 empty] | Agency Priority: | 11
This project renovates the second floor of the Clapp Building on the Missoula campus to complete the HVAC modifications and accomplish the needed code and life safety issues to allow that project to proceed such as asbestos abatement and fire protection renovations. | [7 empty] | Completion Date: | 2011-06-30
Agency No: |  | 5103 |  | Agency Name: |  | THE UNIVERSITY OF MONTANA
Program No: |  | 1 |  | Program Name: |  | INSTRUCTION
This Project: |  |  | Major Maintenance Class: |  |  | Location:
Is an Original Facility |  |  | Class I |  |  | Site on owned property |  | Outside of 100 yr flood plain
Improves an Existing Facility |  |  | Class II |  |  | Site to be selected |  | Utilities already available
Replaces an Existing Facility |  |  | Class III |  |  | Site already selected |  | Access already available
Estimated Cost of Project:
| 1. Land Acquisition: |  |  | 0 |  | 9. Contingency: |  | 120000
| 2. Site Investigation: |  |  | 2500 |  | 10. A&E Supervisory Fee: |  | 30000
| 3. Consultant Services: |  |  | 80000 |  | 11. Construction Mgmt: |  | 0
| 4. Construction Costs: |  |  | 850000 |  | 12. Commissioning: |  | 25000
| 5. Site Development: |  |  | 3500 |  | 13. Construction Testing: |  | 30000
| 6. Utilities: |  |  | 0 |  | 14. Percent for the Arts: |  | 0
| 7. Telecomm. Systems: |  |  | 0 |  | 15. Other: Relocation Expenses |  | 250000
| 8. Furnishings & Equipment |  |  | 0 |  | Total Estimated Cost: |  | 1391000
Project Funding:
|  | Fund | Amount |  | Cash/Bonded |  | Bill Number
|  | 05007 | 1391000 |  | C |  | HB 0005
Total Funding:
1391000
DESCRIPTION OF FACILITY:
General Description: |  |  | This project would complete HVAC improvements and remove remaining asbestos containing materials within the air plenum on the Second Floor of the Clapp Building .
Impact on Existing Facilities: |  |  | In addition to the removal of the remaining friable asbestos, deferred maintenance, and adaptive renovations to the entire facility, the project will complete the remaining HVAC work on the second floor.
Functional Space Requirements: |  |  | N/A
EXPLANATION OF PROBLEM BEING ADDRESSED: |  |  | The poor condition of the asbestos fireproofing on the structural steel, which is in the return air plenum, requires abatement prior to the interior 2nd floor HVAC replacement and for any other renovations, construction or maintenance. This work needs to be coordinated with the mechanical work to limit major disruptions to the occupants and programs to one construction period. To accomplish any work in the facility, there is a need for temporary labs, classrooms and office space for the on-going operations of the building occupants.
ALTERNATIVES CONSIDERED: |  |  | 1. Fully fund the friable asbestos removal, deferred maintenance and adaptive renovations of this facility.
2. Partially fund the asbestos removal, deferred maintenance and adaptive renovations of the second floor with the intention of funding the remaining work in the next biennium.
3. Do nothing and continue accepting the risks to the students, faculty and staff that use this facility.
Rationale for Selection of Particular Alternative: |  |  | Funding the entire request is the alternative which provides for the maximum protection of the occupants health and safety. This is also the most cost effective approach in accomplishing the deferred maintenance, life safety, code, renovations and any other replacements.
GENERAL NARRATIVE: |  |  | Hundreds of state buildings have asbestos in them. The Clapp Building poses unique asbestos related problems not experienced in other state buildings the asbestos is friable. The asbestos fireproofing sprayed on the structural steel in the building is poorly adhered causing it to de-laminate from the steel, falling on top of the ceiling tiles or into rooms where no ceiling tiles exist. The ceiling tiles provide a minimal barrier to contain the asbestos but the tops of all ceiling tiles have to be treated as contaminated with asbestos, as many test results indicate. All work above the ceiling poses a potential risk of exposure to occupants unless great care is taken in the course of the work to safeguard against such exposure.
The rate of de-lamination of the fireproofing is increasing as a result of age and building vibration. To date, air sampling has shown no elevated levels of asbestos fibers in the occupied space and we can say with assurance that we have not so far put occupants health at risk. In order to say that in the future, we will need to continue to do air monitoring and anticipate that at some point, the rate of de-lamination will likely increase such that air-monitoring will show elevated levels that will require emergency evacuation and loss of use of the entire building until such time as the asbestos is abated. In order to avoid this, the friable asbestos fireproofing on the second floor of the Clapp Building needs to be abated now as part of a planned building renovation.
The 55th Legislature originally funded $1.2 M to renovate/replace the Clapp Building's HVAC and lab exhaust systems. The process of designing a replacement program was long and fraught with problems due to the friable asbestos in the building and trying to accomplish these replacements while the building was occupied. The project proceeded and ran into asbestos problems which caused considerable concern to the occupants and pushed university expenditure needs beyond the funding by the State. The result was the third and fourth floor replacements were deferred and additional funding was requested from the 59th Legislature. This funding was granted and in the new design for the third and fourth floor HVAC equipment replacements, it was decided that vacating of all of the occupants was the only acceptable method for the project.
This construction method required the allocation of The University of Montana LRBP code and life safety allocation from the 59th Legislature to supplement the project to remove all of the friable asbestos from the fourth floor. The asbestos abatement and relocation expenses for the fourth floor cost in excess of $750,000.
Now that the fourth and third floors have been abated, it is time to continue with the process on the second floor. While the air handlers have already been replaced on the second floor, most of the beams within the air plenum still have the decaying asbestos fireproofing and much of the duct work and air devices still need to be replaced. This request for $1,391,000 would cover the cost of completing the needed HVAC improvements as well as remove all asbestos contaminated items thus eliminating a health risk to building occupants.
This request is critical because the second floor still has its return air plenum contaminated with friable asbestos which is falling off structural members.
X
X
X
X
X
X
X