## landscape
Long Range Building Program | [8 empty] | 2010-2011 Biennium
Capital Projects Detail
Department: |  | THE UNIVERSITY OF MONTANA
Project Title: |  | Water Infrastructure Upgrades (Missoula) | [5 empty] | Statewide Priority: | NA
Brief Description of Project: | [7 empty] | Agency Priority: | 17
This project will install backflow preventers on the water service entrances from Mountain Water on The University of Montana - Missoula campus. It also will perform a water distribution study, and include some piping upgrades to this system. | [7 empty] | Completion Date: | 2011-06-30
Agency No: |  | 5103 |  | Agency Name: |  | THE UNIVERSITY OF MONTANA
Program No: |  | 1 |  | Program Name: |  | INSTRUCTION
This Project: |  |  | Major Maintenance Class: |  |  | Location:
Is an Original Facility |  |  | Class I |  |  | Site on owned property |  | Outside of 100 yr flood plain
Improves an Existing Facility |  |  | Class II |  |  | Site to be selected |  | Utilities already available
Replaces an Existing Facility |  |  | Class III |  |  | Site already selected |  | Access already available
Estimated Cost of Project:
| 1. Land Acquisition: |  |  | 500000 |  | 9. Contingency: |  | 150000
| 2. Site Investigation: |  |  | 0 |  | 10. A&E Supervisory Fee: |  | 0
| 3. Consultant Services: |  |  | 200000 |  | 11. Construction Mgmt: |  | 40000
| 4. Construction Costs: |  |  | 1000000 |  | 12. Commissioning: |  | 0
| 5. Site Development: |  |  | 80000 |  | 13. Construction Testing: |  | 0
| 6. Utilities: |  |  | 0 |  | 14. Percent for the Arts: |  | 0
| 7. Telecomm. Systems: |  |  | 0 |  | 15. Other: |  | 0
| 8. Furnishings & Equipment |  |  | 0 |  | Total Estimated Cost: |  | 1970000
Project Funding:
|  | Fund | Amount |  | Cash/Bonded |  | Bill Number
|  | 05007 | 1970000 |  | C |  | HB 0005
1970000
DESCRIPTION OF FACILITY:
General Description: |  |  | The University of Montana owns and operates a water distribution system on campus. The water is provided directly from Mountain Water, the sole water utility in the City of Missoula. This water is provided through four service entrances and is distributed throughout campus to buildings and irrigation systems.
Impact on Existing Facilities: |  |  | This project will upgrade the water service and distribution system on campus.
Functional Space Requirements: |  |  | Additional space will likely need to be acquired on which to locate structure(s) to house the protection devices, water booster pumps, and emergency generator.
EXPLANATION OF PROBLEM BEING ADDRESSED: |  |  | The campus uses water supplied directly from Mountain Water Company. Relatively recent changes in law allow Mountain Water to require their customers to install backflow preventers to prevent contamination of Mountain Water's supply system. In 2002 the University attempted to comply with this by installing backflow preventers on the individual buildings on campus. Mountain Water had preferred that UM install backflow preventers at the service entrances, directly after the meters. This solution was not chosen because it would have detrimentally affected the water pressure on campus and thus the integrity of the fire suppression systems. Recent developments indicate that the backflow preventers installed on the buildings likely do not meet Mountain Water's requirements, nor do they likely meet DEQ regulations. The regulations require that an inspection verify that no cross connections exist between the water distribution system and all of the cooling wells on campus. Because the distribution system is buried, it would be virtually impossible to verify this without major excavations throughout campus.
Without this verification, the only viable solution seems to be installing backflow preventers at the service entrances.
ALTERNATIVES CONSIDERED: |  |  | 1. Leave the system alone and risk inadequate fire protection and water supply systems, and also accept the risk that Mountain Water will refuse to provide water to the University.
2. Partially fund the project and accept some of the risk noted.
3. Fund the requested project fully and ensure continued supply of water to the University.
Rationale for Selection of Particular Alternative: |  |  | Funding the entire request is the alternative which provides the most straightforward and cost effective solution to the issues at hand.
GENERAL NARRATIVE: |  |  | Because of the noted deficiencies, the University's ability to procure water from Mountain Water is at risk. This project will design and implement a system of backflow preventers which will cause the University to be in full compliance and ensure uninterrupted operation of campus. The hydraulic study that will be necessary to design and size the system will also be a useful tool to evaluate the entire water distribution system on campus for appropriate sizing of piping and service lines, especially given the recent and planned expansions and new buildings. It is anticipated that some distribution system work will also take place to address deficiencies noted in the hydraulic study. Additional looping of the distribution system may also be appropriate.
Each of the service entrances to campus is located in a congested area, often in the middle of a street. Installing the facilities to house these new backflow preventers, booster pumps, and emergency generators will be challenging given the lack of space. Significant modification to the water service inlets to campus may be necessary in addition to possibly needing to purchase adjacent property.
x
X
x
X
X
X
X